## TC
BISHOP'S CASTLE CLIMATE ACTION PLAN: QUARTERLY REPORT APRIL 2024
TOWN COUNCIL ACTIONS
| Actions | Year | Status | Updates
1 | Publicise BCTC’s [Bishop’s Castle Town Council] commitment to mitigating climate change, and add ‘Climate & Environment’ as a standard Agenda item. | 1,2,3 | √ | Year 1 completed, remains on-going for Years 2&3 Evidence: Carbon Footprint audit, sponsoring ‘Going Wild’ and Environment Festival
2 | Create a climate emergency page on the BCTC website; | 1 | √ | Year 1 Completed. Evidence: Link to Light Foot website inserted on Town Council’s website.
3 | Encourage litter picking & review litter bin locations and types | 1,2,3 | √ | Year 1 completed. Remains on-going for Years 2 & 3
4 | Undertake a Carbon Footprint Audit on all Council activities. Annual review to identify reductions. Put report on Council web site. | 1,2,3 | √ | Year 1 completed. To be updated August 2024. See here for Scope [i] Evidence: Ideally, report posted on Council website
5 | Hold paperless Council meetings | 1,2,3 | √ | Done –where possible. Monitor for years 2 & 3
6 | Encourage a long-term approach to tree planting and identification for bulk planting | 2,3 |  | Year 1, Agreed that two Charter Oaks are to be planted in Playing Fields Evidence: Photo of trees to be taken & put on website
7 | Review Report quarterly against the plan | 1,2,3, | √ | Year 1 CAG Reports submitted in October & January. Final Report in April 24. Evidence: Reports on Light Foot [& Town Council’s website?] and referenced in Town Council’s Minutes
8 | Add climate emergency references to all new contract specifications and tenders and include in evaluation process | 2 |  | Evidence: Produce draft of a standard statement for inclusion in contracts stating that it will form part of the evaluation
9 | Town Council to ensure its electricity supplier is 100% renewable; | 3 |  | Year 1: Started – Oct 23 Evidence: Publish name of supplier
10 | Encourage contractors to have ‘zero to landfill’ policies | 3 |  | Produce draft of question to be issued to all contractors Evidence: Record responses from contractors in TC’s Minutes.
11 | Ensure use of peat-free compost | 1,2,3 |  | Allotments made aware – Oct 23. Explore further opportunities, e.g planters and Council land. Evidence: Feedback to be sought from TC’s new Environment & Nature Agenda item
12 | Investigate the requirements of emergency planning for extreme events | 3 |  | Explore Shropshire Council Emergency Planning. Identify our concerns, e.g. extreme winter conditions, flooding, power cuts, etc. Evidence: Draft mitigation plan
13 | BCTC will commission CAG to undertake an annual Town carbon footprint and to propose targets for the Town to reduce its collective carbon emissions. One action from the ‘Personal Actions’ list to be included in each Town Newsletter. | 1,2,3 |  | Evidence: CAG Report and Newsletter Actions.
14 | BCTC will press for changes to ensure that all planning applications (e.g. housing, transport, sewage) are amended to minimise carbon emissions and other impacts on the environment/climate 2024 – CAG to produce for councillors a tick list to be used when considering such applications | 1,2,3 |  | Evidence: Agreed Tick-list. Recorded in Planning Application discussions in Town Council’s Minutes Note: Tick-list to reference Bio-diversity Net Gain Legislation in which developments must result in a better quality natural habitat than there was before the development took place (but not necessarily in the same place)
15 | BCTC will track Shropshire Council’s climate actions to adopt where appropriate | 2 |  | Evidence: Add new ideas to Quarterly Reports to Town Council
16 | BCTC will encourage Shropshire Council to seek funding from the ‘Marches Forward Partnership’ to assist with making transformative changes to ameliorate climate and nature breakdown. | 2 |  | A new coalition of Monmouthshire, Powys, Herefordshire & Shropshire Councils. Evidence:
17 | BCTC will ensure its Contractors stop using neonicotinoid pesticides (e.g ‘Round-up’ & ‘Glyphosate’) and press Shropshire Council to also stop using them to ameliorate insect species loss. | 2 |  | Evidence: TC approval to be recorded in TC’s Meeting Minutes
18 | BCTC will support the CAG’s objective of community land acquisition to use for wellbeing, Nature Recovery and ‘Right to Grow’ purposes | 3 |  | Evidence: Consideration by TC of any suggestions put forward.
TC ACTIONS NOT LISTED IN CAP
£500 grant for Environment Fair 2024

## CAG
CLIMATE ACTION GROUP ON-GOING PROJECTS
| Action | Year |  | Update
1 | Continuously monitor & update CAP | 2,3 | √ | Part 1 Update for 24-25 approved by Town Council
2 | Explore means of progress CAP Part 2 Actions when resources allow | 2,3 |  | Evidence: Assess when undertaking review & update of Part 2
3 | Continue delivering the ‘Going Wild in BC’ project’s Stage 2 | 2 | √ | NHLC Grant of £330k. Project Co-ordinator recruited.
4 | Continue progressing the ‘Community Heat Network’ | 2 | √ | 100K grant received for next stage activities
5 | Seek funding for Heat Network Household Energy Surveys | 2 | √ | MEA have received funding for Shropshire. This is no longer an action
6 | Maintain BC Freegle | 2,3 | √ | Evidence: Continue on-line mediation of posts. (Now in Year 11)
7 | Organize and run an ‘Environment Day’ | 1,2,3 | √ | Evidence: Year 1 delivered. Year 2 planned to address all aspects of waste (cf. Festival of Thrift).
8 | Explore Citizens’ Jury on Climate & Bio-diversity | 3 |  | Evidence: Outcome of Jury discussion
9 | Explore community land acquisition for wellbeing, Nature Recovery and ‘Right to Grow’ purposes | 2,3 |  | Evidence: Publicity and initiative reports to TC