## ACTIONS
BISHOP'S CASTLE CLIMATE ADAPTATION PLAN - QUARTERLY REPORT APRIL 2025
TOWN COUNCIL ACTIONS - WITH YEAR 3 UPDATES
1 | Communicate BCTC’s [Bishop’s Castle Town Council] commitment to mitigating/adapting to the Climate & Nature Crisis, and add ‘Climate & Environment’ as a standard Agenda item. Boost comms for Year 3, e.g Joint TC-CAG Newsletter items. | 1,2,3 | √ | Year 1 & 2 completed, remains on-going for Year 3 Evidence: Council & Town Carbon Footprint audits, sponsoring ‘Going Wild’ and Environment Festival Climate & Nature Agenda items introduced in September 24.
2 | Create a climate emergency page on the BCTC website. Bring website up-to-date for Year 3. | 1 | √ | Year 1 Completed. Evidence: Link to Light Foot website inserted on Town Council’s website. Year 2: static, lack of information.
3 | Encourage litter picking & review litter bin locations and types. For Year 3 Acknowledge Litter Pickers and explore 'Landfill' bin labels. | 1,2,3 | √ | Year 1 & 2 completed. Remains on-going for Year 3
4 | Undertake a Carbon Footprint Audit on all Council activities. Annual review to identify reductions. Put report on Council web site. | 1,2,3 | √ | Year 1 & 2 completed, Year 3 to be produced. Evidence: Reports posted on Town Council website
5 | See Archive
6 | Encourage a long-term approach to tree planting and identification for bulk planting. For Year 3: Create a Directory of Groups & acknowledge work done. | 2,3 | √ | Year 1, Agreed that two Charter Oaks are to be planted in Playing Fields. Year 2, Harriet Carty and the Mayor have agreed a Playing Fields plan. Leon has discussed 'greening' for the Tennis Courts. Evidence: Photo of trees to be taken & put on website
7 | Review CAP Report quarterly against the plan | 1,2,3, | √ | Year 1 CAG Quarterly Reports submitted in Oct, Jan 23 & April 24. Year 2 Reports July, Oct 24 & Jan & April 25. Evidence: Reports on Light Foot & Town Council’s website and referenced in Town Council’s Minutes
8 | Add climate emergency references to all new contract specifications and tenders and ensure Contractors stop using neonicotinoid pesticides. Include in evaluation process | 3 |  | Moved from Year 2 to Year 3. Evidence: Produce draft of a standard statement for inclusion in contracts stating that it will be a key factor in award evaluation
9 | Town Council to ensure its electricity supplier is 100% renewable; | 3 |  | Moved from Year 2 to Year 3 Evidence: Publish name of supplier
10 | Encourage contractors to have ‘zero to landfill’ policies | 3 | √ | Evidence: Record responses from contractors in TC’s Minutes.
11 | Encourage use of peat-free compost | 1,2,3 |  | Allotments made aware – Oct 23. Explore further opportunities, e.g planters and Council land. Evidence: Feedback to be sought from TC’s new Environment & Nature Agenda item
12 | Investigate the requirements of emergency planning for extreme events | 3 |  | Identify subject for next Town Forum, e.g. extreme winter conditions, flooding, power cuts, food supply, etc. Evidence: Resilience Adaptation Plan
13 | BCTC will commission CAG to undertake an annual Town carbon footprint and to propose targets for the Town to reduce its collective carbon emissions. | 1,2,3 | √ | 2 year's measurements taken so far. Third to be produced in Year 3. Evidence: Town Carbon footprint graphic
14 | BCTC will press for changes to ensure that all planning applications (e.g. housing, transport, sewage) are amended to minimise carbon emissions and other impacts on the environment/climate | 1,2,3 |  | Evidence: Agreed Tick-list. Recorded in Planning Application discussions in Town Council’s Minutes Note: Tick-list to reference Bio-diversity Net Gain Legislation in which developments must result in a better quality natural habitat than there was before the development took place (but not necessarily in the same place)
15 | BCTC will track Shropshire Council’s climate actions to adopt where appropriate | 2 |  | Evidence: Add new ideas to Quarterly Reports to Town Council
16 | DELETED - SEE ARCHIVE
17 | SEE ARCHIVE. MERGED WITH ACTION 8
18 | BCTC will support the CAG’s objective of community land acquisition to use for wellbeing, Nature Recovery and ‘Right to Grow’ purposes | 3 |  | For example, Civil Defence Bowling Club Evidence: Consideration by TC of any suggestions put forward.
19 | NEW: Management Plan for Market Square | 3 |  | In collaboration with Going Wild Evidence: draft Management Plan
20 | NEW: Garden Contractors guidelines | 3 |  | To avoid over-enthusiastic cutting back of shrubs, hedges, etc. (cf. hospital) Evidence: Instructions that ensure work is done correctly.
21 | NEW: Management Plan for Town's Planters | 3 |  | In collaboration with Going Wild Evidence: draft Management Plan
TOWN COUNCIL ACTIONS NOT LISTED IN CAP
April 24 | £500 Grant for 2024 Environment Fair
April 24 | £1000 grant for Going Wild Kids' Club
June 24 | Commissioning report on BC Festivals Waste Management
Sept 24 | Added Climate & Bio-diversity as a standard Town Council agenda item
Sept 24 | Inserting articles on Bio-divesity actions in the Town's newsletter
CLIMATE ACTION GROUP ON-GOING PROJECTS
1 | Continuously monitor & update CAP | 2,3 | √ | Part 1 Update for 24-25 approved by Town Council
2 | Explore means to progress CAP Part 2 Actions when resources allow | 2,3 |  | Evidence: Assess when undertaking review & update of Part 2
3 | Continue delivering the ‘Going Wild in BC’ project’s Stage 2 (including Kids Club) | 1,2,3 | √ | Evidence: CAG reports containing Going Wild updates to be included with Quarterly Reports
4 | Continue progressing the ‘Community Heat Network’ | 1,2,3 | √ | Stage 2 studies completed and Wind Turbine planning application submitted on 15th January 25. Evidence: Planning Application details publicised widely
5 | Seek funding for Heat Network Household Energy Surveys | 2 | √ | Evidence: If successful, re-publicise survey opportunities
6 | Maintain BC Freegle | 1,2,3 | √ | Evidence: Continue on-line mediation of posts. (Now in Year 12)
7 | Organize and run an ‘Environment Day’ | 2,3 | √ | Evidence: Year 1 & 2 delivered.
8 | Explore Citizens’ Jury on Climate & Bio-diversity | 3 | √ | Town Discussion' on local food resilience to take place on 20th January. Others to follow. Evidence: Report on outcome of discussion
9 | Explore community land acquisition for wellbeing, Nature Recovery and ‘Right to Grow’ purposes | 2,3 |  | E.g. Civil Defence Bowling Club initiative Evidence: Publicity and initiative reports to TC
CAG ACTIONS NOT LISTED IN CAP
1 | Community Shop initiative | 2 |  | Progress halted while under review.
2 | Explore Civil Defence Bowling Green | 2,3 | √ | Details passed to Town Council. CAG to produce suggestions for utilising the site.
3 | Waste management at Carnival | 2 | √ | Waste collection points erected and waste disposed of. Useful lessons learned and report produced for Town Council.
4 | Green Plaque initiative | 2,3 | √ | Underway. Exploring possible 'Community Green Plaque' award for Bishop's Castle
5 | River pollution monitoring | 2,3 | √ | Underway.TC equipment request turned down. Alternative funding being. Briefing Paper sent to TC.
6 | Air pollution | 2,3 | √ | Monitor installed. Awaiting technical support for history download
7 | Lightfoot Relaunch (20th anniversary) | 2 | √ | Stars Pop-up shop, 13 - 18 January
8 | Hold BC Resilience/Adaption Town Forums h Town Council | 3 | √ | Year 2 Food Resilience Forum held in January. Subject for next Forum to be agreed with Town Council.

## ARCHIVE
5 | Hold paperless Council meetings | 1,2,3 | √ | Done as far as possible for now.
17 | BCTC will ensure its Contractors stop using neonicotinoid pesticides (e.g ‘Round-up’ & ‘Glyphosate’) and press Shropshire Council to also stop using them to ameliorate insect species loss. | 2 |  | MERGED WITH ACTION 8 Evidence: TC motion to be approved and recorded in TC’s Meeting Minutes
16 | BCTC will encourage Shropshire Council to seek funding from the ‘Marches Forward Partnership’ to assist with making transformative changes to ameliorate climate and nature breakdown. | 2 |  | A new coalition of Monmouthshire, Powys, Herefordshire & Shropshire Councils. Evidence:?